## Zone Summary
Building | Zone | Floor | Start | Finish | Span (days) | Activities | Critical Phases | Near-Critical | Risk Level | Latest Critical Phase
CP1 | CP1(Assembly) | GF | 2025-09-04 | 2027-11-01 | 788 | 410 | 1 | 0 | LOW | 9. VOC environmental permit
CP1 | CP1(Calendering) | GF | 2025-09-04 | 2027-07-07 | 671 | 372 | 2 | 0 | HIGH | 8. Submission of completion documents
CP1 | CP1(Coating) | GF | 2025-10-03 | 2028-01-17 | 836 | 367 | 1 | 0 | LOW | 9. VOC environmental permit
CP1 | CP1(Mixing) | GF | 2025-09-04 | 2027-12-18 | 835 | 467 | 1 | 0 | LOW | 9. VOC environmental permit
CP1 | CP1(Mixing) (1'st F) | FF | 2025-10-03 | 2028-02-01 | 851 | 330 | 2 | 0 | HIGH | 8. Submission of completion documents
CP1 | CP1(Notching&Staking) | GF | 2025-11-21 | 2027-10-24 | 702 | 363 | 2 | 0 | HIGH | 8. Submission of completion documents
CP1 | CP1(Slitting) | GF | 2025-09-04 | 2027-08-10 | 705 | 331 | 2 | 0 | HIGH | 8. Submission of completion documents
FA1 | FA1 (M1) | FF | 2025-08-30 | 2027-04-23 | 601 | 101 | 1 | 0 | LOW | 4. CDR Readiness for Equipment Move in
FA1 | FA1 (M1) | GF | 2025-03-15 | 2027-10-11 | 940 | 276 | 1 | 0 | LOW | 13. VOC environmental permit
FA1 | FA1 (M2) | FF | 2025-08-31 | 2028-03-19 | 931 | 41 | 1 | 0 | LOW | 13. VOC environmental permit
FA1 | FA1 (M2) | GF | 2025-03-15 | 2027-07-19 | 856 | 262 | 1 | 1 | MED | 3-3. HVAC Equipment install
FA1 | FA1 (M3) | FF | 2025-08-30 | 2027-09-18 | 749 | 95 | 1 | 1 | MED | 4. CDR Readiness for Equipment Move in
FA1 | FA1 (M3) | GF | 2025-03-15 | 2028-03-07 | 1088 | 303 | 1 | 0 | LOW | 13. VOC environmental permit

## Critical Path Detail
Zone | Floor | Phase | Start | Finish | Duration (days) | Slack (days) | Status | Activity Count
CP1(Assembly) | GF | 9. VOC environmental permit | 2027-07-04 | 2027-11-01 | 120 | 0 | CRITICAL | 2
CP1(Calendering) | GF | 8. Submission of completion documents | 2027-02-07 | 2027-07-07 | 150 | 0 | CRITICAL | 5
CP1(Calendering) | GF | 9. VOC environmental permit | 2027-03-09 | 2027-07-07 | 120 | 0 | CRITICAL | 2
CP1(Coating) | GF | 9. VOC environmental permit | 2027-09-19 | 2028-01-17 | 120 | 0 | CRITICAL | 2
CP1(Mixing) | GF | 9. VOC environmental permit | 2027-08-20 | 2027-12-18 | 120 | 0 | CRITICAL | 2
CP1(Mixing) (1'st F) | FF | 8. Submission of completion documents | 2027-09-04 | 2028-02-01 | 150 | 0 | CRITICAL | 4
CP1(Mixing) (1'st F) | FF | 9. VOC environmental permit | 2027-10-04 | 2028-02-01 | 120 | 0 | CRITICAL | 2
CP1(Notching&Staking) | GF | 8. Submission of completion documents | 2027-05-27 | 2027-10-24 | 150 | 0 | CRITICAL | 4
CP1(Notching&Staking) | GF | 9. VOC environmental permit | 2027-06-26 | 2027-10-24 | 120 | 0 | CRITICAL | 2
CP1(Slitting) | GF | 8. Submission of completion documents | 2027-03-13 | 2027-08-10 | 150 | 0 | CRITICAL | 4
CP1(Slitting) | GF | 9. VOC environmental permit | 2027-04-12 | 2027-08-10 | 120 | 0 | CRITICAL | 2
FA1 (M1) | FF | 4. CDR Readiness for Equipment Move in | 2025-08-30 | 2027-04-23 | 601 | 0 | CRITICAL | 11
FA1 (M1) | GF | 13. VOC environmental permit | 2027-06-13 | 2027-10-11 | 120 | 0 | CRITICAL | 1
FA1 (M2) | FF | 13. VOC environmental permit | 2027-11-20 | 2028-03-19 | 120 | 0 | CRITICAL | 1
FA1 (M2) | GF | 3-3. HVAC Equipment install | 2026-07-15 | 2027-07-19 | 369 | 0 | CRITICAL | 38
FA1 (M2) | GF | 2. Construction (Ground Floor) | 2026-04-01 | 2027-06-19 | 444 | 30 | NEAR-CRITICAL | 70
FA1 (M3) | FF | 4. CDR Readiness for Equipment Move in | 2025-08-30 | 2027-09-18 | 749 | 0 | CRITICAL | 11
FA1 (M3) | FF | 2-1. Construction (First Floor) | 2026-03-13 | 2027-09-03 | 539 | 15 | NEAR-CRITICAL | 84
FA1 (M3) | GF | 13. VOC environmental permit | 2027-11-08 | 2028-03-07 | 120 | 0 | CRITICAL | 1

## Project Critical Path
Rank | Zone | Floor | Finish Date | Gap to Project (days) | Status | Driving Phase
1 | FA1 (M2) | FF | 2028-03-19 | 0 | PROJECT CP | 13. VOC environmental permit
2 | FA1 (M3) | GF | 2028-03-07 | 12 | NEAR-CP | 13. VOC environmental permit
3 | CP1(Mixing) (1'st F) | FF | 2028-02-01 | 47 |  | 8. Submission of completion documents
4 | CP1(Coating) | GF | 2028-01-17 | 62 |  | 9. VOC environmental permit
5 | CP1(Mixing) | GF | 2027-12-18 | 92 |  | 9. VOC environmental permit
6 | CP1(Assembly) | GF | 2027-11-01 | 139 |  | 9. VOC environmental permit
7 | CP1(Notching&Staking) | GF | 2027-10-24 | 147 |  | 8. Submission of completion documents
8 | FA1 (M1) | GF | 2027-10-11 | 160 |  | 13. VOC environmental permit
9 | FA1 (M3) | FF | 2027-09-18 | 183 |  | 4. CDR Readiness for Equipment Move in
10 | CP1(Slitting) | GF | 2027-08-10 | 222 |  | 8. Submission of completion documents
11 | FA1 (M2) | GF | 2027-07-19 | 244 |  | 3-3. HVAC Equipment install
12 | CP1(Calendering) | GF | 2027-07-07 | 256 |  | 8. Submission of completion documents
13 | FA1 (M1) | FF | 2027-04-23 | 331 |  | 4. CDR Readiness for Equipment Move in